1. What CDC actually needs (30 seconds of framing, then the four that matter)

Frame: "This is CDC's central vaccine ordering platform — Awardees ordering on behalf of providers nationwide. Four requirements drive everything else:"

- External-user order lifecycle — Awardees must create, search, display, and cancel orders in S/4. They are customers, not internal staff.

- Financial control — cancellation releases committed budget and SPC allocation instantly. Role rules differ pre- vs. post-approval and direct-ship vs. not. Get this wrong = incorrect budget releases. It's a compliance control, not a UI feature.

- Jurisdiction isolation — Awardees see only their own data. Federal system, external users.

- Four entry channels, one rulebook — Fiori UI, machine API, EXiS, provider-originated. Identical validations everywhere.

Plus the operational layer: inline Inventory-on-Hand during ordering, fix-and-resubmit for soft-stop rejections, copy order with CDC fund rules, and — found in the BPD — un-cancel of shipped lines so ASNs can post.

2. CRM_UI today vs. F3893

- Today: one working surface — header, items, IoH, shipping all visible, minimal clicks. Users are fast and fluent in it.

- F3893 spreads that across object-page tabs. The customer called it "clunky" — that wasn't a taste complaint, it's the paradigm: more navigation, more clicks per order.

- Deeper mismatch: F3893 is built for internal sales representatives — SAP's own docs say so, with a limited order-type and field set. Our users are external customers. There's a live SAP Community case of a team failing to even restrict F3893 data per logged-in external customer.

3. The gaps with the F3893 route (severity order)

- Critical: no external-customer data-isolation model; no CDC cancellation matrix; no inline IoH in order creation.

- High: the click-heavy tab flow itself; limited types/fields; deep extensions are upgrade-fragile — there's a documented case where a BAdI added for an extended copy of F3893 broke order creation in the standard app.

- Med: no copy-with-CDC-exceptions, no un-cancel, no budget-bypass replacement, search doesn't match the spec's operators and cascading lookups.

- Punchline: "These gaps are behavioral, not cosmetic. Key-user extensibility adds fields; it doesn't add workflows."

4. Proposed solution and why it beats adaptation

- One rules engine (RAP behavior layer) over the standard sales order API — validations, cancellation matrix, jurisdiction security enforced once, for every channel. This is the only design where the budget-release risk can't arise from channel drift.

- Purpose-built ordering cockpit (freestyle SAPUI5): whole order on one screen, fields lock/unlock by status. Click-parity with CRM_UI is a measured acceptance criterion, validated on prototypes with real users — adoption is engineered, not hoped for.

- Standard SAP search component (Fiori Elements List Report) — nearly free, full operator set, saved searches, Excel export. We use standard where standard fits.

- API channel from the same engine at marginal cost — async submit-and-poll matching the BPD's status-service pattern.

- Why not adaptation: pay once vs. pay forever. Every SAP upgrade re-validates a fragile extension mesh, for the platform's life. Orders remain real SD documents (visible in VA02/VA03, standard fulfillment untouched) — clean-core aligned, upgrade-safe.

5. High-level architecture (walk the diagram slide top-down)

Users → Launchpad → three consumption apps (cockpit, search, API channel) → service bindings → one wide RAP behavior box — say "everything funnels through this one enforcement surface" — → E006 rules / E007 IoH integrations → standard SD tables, no custom order tables → fulfillment chain unchanged below the line.

6. Numbers (have ready; lead with mid)

- Core build: 252–404 PD, mid ~328. Fully loaded with levers: ~360–570 PD, mid ~465 ≈ 26 person-months. ROM class, −25/+75%, revised at detailed tech spec.

- Team: ~5 — 1 architect (part-time), 2 RAP, 2 UI5. ~5–7 elapsed months build+test at mid.

- Cushions, be transparent: 10% RAP ramp-up (drops to zero with experienced leads), 12% PM/architecture, 15% ROM contingency that retires at the detailed-spec gate. Two scope toggles priced separately: un-cancel and the API channel — pending open-item decisions, leadership can see their cost live.

- ~40% is backend and invisible — pre-empt it: "that's the rules engine; it's why the API channel costs 14–23 PD instead of a second build, and where the budget-control risk is retired."

- If asked how to go faster: (1) a 3–5 PD spike now on the unmanaged-buffer pattern — collapses the widest estimate range before commitment; (2) close the three blocking open items this month (status dictionary, un-cancel scope, auth concept) — those gate build start more than headcount does; (3) staff one RAP-experienced lead — kills the 10% ramp lever; (4) phase it: search List Report + display ship early while the cockpit hardens; (5) trim scope via the toggles if leadership defers un-cancel — but say plainly that adding developers past ~5 won't compress much; the critical path is decisions and the cockpit, not typing speed.

Three closers to have loaded: "Isn't custom riskier?" — the risk already materialized: the standard app failed user evaluation; we're de-risking with prototype validation and a measurable click criterion. "Why not try harder to extend F3893?" — the gaps are workflow-level, and extension effort at that depth approaches custom cost while keeping upgrade fragility forever. "What do you need from us today?" — endorsement of the direction, plus owners and dates for the three blocking open items.