## ROM Estimate
E008 Custom Vaccine Ordering Application — ROM Development Estimate
Basis: E008 Solution Functional Specification (DRAFT 07/24/2026). Accuracy class: ROM (-25% / +75%). Person-days (PD) = 8 productive hours.
Blue cells are input estimates — adjust per line; all subtotals/totals recalculate. Yellow cells are global levers.
1. RAP Behavior Layer (backend)
# | Work Item | Low (PD) | High (PD) | Mid (PD) | Notes / Drivers
1.1 | BO design; CDS interface & projection views (cockpit + search projection) | 10 | 16 | 13 | Vaccine Request TP model over I_SalesDocument*; search projection sized after OI-5 load figures
1.2 | Unmanaged CRUD: create/update/read mapping to standard SD order API; transactional buffer; late numbering | 16 | 26 | 21 | Highest-uncertainty backend item; includes VBKD/partner/user-status handling
1.3 | E006 validation integration on save/resubmit (hard/soft stop mapping, message container) | 8 | 13 | 10.5 | Assumes E006 exposes a callable rule interface; if not, add integration design effort
1.4 | Determinations (Channel, Employee Responsible, defaults, currency) | 3 | 5 | 4
1.5 | Dynamic feature control from status dictionary (field-level x status x role) | 8 | 13 | 10.5 | Blocked until OI-1 status dictionary ratified
1.6 | Instance authorization (jurisdiction: Grantee↔Sales Office) + action-level auth | 7 | 11 | 9 | Includes negative-path tests for direct OData bypass (Test 19)
1.7 | Action: copyOrder incl. fund-split repopulation & ancillary-kit re-application | 8 | 13 | 10.5 | Exceptions live in the action (E013/E014/E024 calls)
1.8 | Actions: cancelOrder / cancelItem incl. matrix + direct-ship PO/PR cascade | 10 | 16 | 13 | PO/PR cascade for CDC direct-ship cancel is the driver
1.9 | Action: unCancelItem (CDC) incl. budget/SPC re-commitment call + notification + audit | 6 | 12 | 9 | CONDITIONAL — pending OI-2 scope confirmation; excluded via toggle on Summary
1.10 | Actions: createReturn / createReplacement (budget bypass) / resubmit / print trigger | 10 | 16 | 13 | Replacement modeled as distinct role-bound action
1.11 | EML unit test suite (validations, matrix, actions) | 10 | 15 | 12.5 | Exit criterion for behavior layer
| Subtotal — Backend | 96 | 156 | 126
2. Freestyle Cockpit (SAPUI5, OData V4)
# | Work Item | Low (PD) | High (PD) | Mid (PD) | Notes / Drivers
2.1 | App shell, routing, V4 model setup, layout skeleton (single working surface) | 5 | 8 | 6.5
2.2 | Header section: provider entry/roundtrip/read-only, address generation, contact popup, defaults | 10 | 15 | 12.5 | Contact popup with main-contact pinning per FSD
2.3 | Items table: interdependent enablement (Qty→Fund Type), NDC derivations, line rules | 12 | 18 | 15 | Side-effect driven; ancillary/special-circumstance messages surfaced per line
2.4 | Inventory on Hand block: Edit List, insert/delete rows, touched-line rule | 8 | 12 | 10 | Reuses E007 consignment read; E007 interface assumed available
2.5 | Shipping / Alt-Shipping / Org Data / Transactions / History sections | 6 | 10 | 8 | Mostly display + dropdowns
2.6 | Cascading custom value helps (Provider, ER+user, NDC 4-condition, Contact 1a–1e, Ship-to, Created By) | 13 | 20 | 16.5 | Largest single frontend item; Contact help alone has 5 sub-dialogs; built as shared fragments
2.7 | Message handling, side effects, unsaved-changes guard, action wiring (copy/cancel/un-cancel/return/replacement/resubmit/print) | 9 | 14 | 11.5
2.8 | Section 508 implementation pass + screen-reader fixes | 5 | 8 | 6.5 | Standard controls keep this bounded; budget covers labeling/focus/order fixes
2.9 | QUnit/OPA5 test suite | 8 | 12 | 10
| Subtotal — Cockpit | 76 | 117 | 96.5
3. Search & List (Fiori Elements V4 List Report)
# | Work Item | Low (PD) | High (PD) | Mid (PD) | Notes / Drivers
3.1 | List Report app, annotations, filter fields + condition operators, variants, Excel export, navigations | 6 | 9 | 7.5 | Near out-of-box; per-field operator sets via filter restrictions
3.2 | Custom filter value helps (reuse of 2.6 fragments) + result-list layout per FSD | 3 | 5 | 4
| Subtotal — Search & List | 9 | 14 | 11.5
4. Machine API Channel (conditional — OI-4)
# | Work Item | Low (PD) | High (PD) | Mid (PD) | Notes / Drivers
4.1 | Web API service binding, communication scenario/arrangement, interface-user auth mapping | 5 | 8 | 6.5 | Same behavior layer; binding + comm setup only
4.2 | Async contract: acceptance + correlation ID, Status Service integration, message payloads | 6 | 10 | 8 | Assumes Status Service API is a shared platform object; if E008-owned add 8–12 PD
4.3 | API documentation + consumer test harness (EXiS integrators) | 3 | 5 | 4
| Subtotal — API Channel | 14 | 23 | 18.5
5. Cross-Cutting & Deployment
# | Work Item | Low (PD) | High (PD) | Mid (PD) | Notes / Drivers
5.1 | Fiori launchpad content: catalogs, groups/spaces, tiles, target mappings; PFCG roles (2 tiers) | 4 | 6 | 5 | Provider tier explicitly excluded
5.2 | ATC/CI setup (S/4 readiness variants), transports, landscape moves | 3 | 5 | 4
5.3 | Performance validation of search projection & value helps (after OI-5 figures) | 3 | 6 | 4.5
| Subtotal — Cross-Cutting | 10 | 17 | 13.5
6. Design, Documentation & Validation
# | Work Item | Low (PD) | High (PD) | Mid (PD) | Notes / Drivers
6.1 | Technical specifications (backend, cockpit, API) from this solution spec | 9 | 13 | 11 | The 'detailed technical specs' phase you named; estimate revision included
6.2 | UX design + interactive prototype + 2 customer validation cycles (click-economy baseline, Test 25) | 8 | 13 | 10.5 | Prototype-based validation is the insurance policy on the 'clunkiness' complaint
6.3 | Status dictionary / auth concept workshops & sign-off support (OI-1/2/3) | 4 | 7 | 5.5
| Subtotal — Design & Docs | 21 | 33 | 27
7. Testing & Stabilization (beyond unit tests)
# | Work Item | Low (PD) | High (PD) | Mid (PD) | Notes / Drivers
7.1 | FUT execution (scenarios 1–25) + defect resolution | 12 | 20 | 16
7.2 | SIT support (E006/E007/EDI/API touchpoints) + defect resolution | 8 | 14 | 11 | Un-cancel/ASN scenario is cross-object — SIT is where it proves out
7.3 | UAT support + fixes + 508 verification | 6 | 10 | 8
| Subtotal — Test & Stabilization | 26 | 44 | 35
Summary
# | Work Item | Low (PD) | High (PD) | Mid (PD) | Notes
| Backend | 96 | 156 | 126
| Cockpit | 76 | 117 | 96.5
| Search & List | 9 | 14 | 11.5
| API Channel | 14 | 23 | 18.5
| Cross-Cutting | 10 | 17 | 13.5
| Design & Docs | 21 | 33 | 27
| Test & Stab. | 26 | 44 | 35
| Core total (before levers) | 252 | 404 | 328
Global Levers (yellow = adjust)
| RAP/V4 ramp-up uplift (%) | 10% |  |  | Set 0% if team is RAP-experienced; 10–15% if SEGW-native (applies to Backend+Cockpit+Search+API)
| PM / architecture oversight (%) | 12% |  |  | Applied to core + ramp-up
| ROM contingency (%) | 15% |  |  | Estimation-maturity reserve at ROM stage; retire at detailed-spec revision
| Include FR-04 Un-Cancel (1=yes, 0=no) | 1 |  |  | Pending OI-2; set 0 to see estimate without it
| Include API channel (1=yes, 0=no) | 1 |  |  | Pending OI-4 RICE ownership decision
Adjusted Totals
# | Work Item | Low (PD) | High (PD) | Mid (PD) | Notes / Drivers
| Core after scope toggles | 252 | 404 | 328
| + Ramp-up uplift | 25.2 | 40.4 | 32.8
| + PM / architecture | 33.264 | 53.328 | 43.296
| + Contingency | 46.5696 | 74.6592 | 60.6144
| TOTAL (person-days) | 357.0336 | 572.3872 | 464.7104
| ≈ Person-months (18 PD/month) | 19.8352 | 31.7993 | 25.8172
Indicative duration: with 1 architect (50%), 2 backend, 2 UI5 developers ≈ 5–7 elapsed months build+test at mid estimate, excluding design-phase lead time and OI resolution.

## Assumptions & Exclusions
Assumptions
• Accuracy: ROM class, -25% / +75%. Estimates revise at detailed technical spec completion (item 6.1).
• E006 exposes callable validation/cancellation rule interfaces with stable signatures; rule CONTENT effort sits in E006, not here.
• E007 consignment/IoH pre-population logic is available as a reusable interface for the IoH block.
• Sales order type, item categories, ratified user status profile, partner determination, and pricing config are delivered by the config workstream before backend build (FSD assumptions).
• Status dictionary (OI-1) and authorization concept (OI-3) are signed before field-control and auth build start; delays shift 1.5/1.6.
• Status Service API is a shared platform object; if E008-owned, add 8–12 PD to 4.2.
• Business Partner master data (providers, contacts, awardees) migrated and consumable by value helps in the dev/test landscape.
• One production locale (EN); message classes translation-ready but no translation effort included.
• Team: 1 solution architect (part-time), 2 ABAP/RAP developers, 2 SAPUI5 developers, shared QA. Ramp-up lever covers RAP/V4 learning if applicable.
• Person-day = 8 productive hours; person-month = 18 PD.
Exclusions
• E006/E007/E010/E011/E013/E014/E024 rule and object content; C001–C006 BP objects; E001 marketing attributes.
• SD configuration, output/forms template development (E008 keeps the print trigger only — OI-6), EDI/fulfillment chain (Migrate scope).
• Data migration, cutover, and legacy CRM decommissioning.
• End-user training content and delivery (BPD revision for training references is OI-7, effort with process team).
• Hypercare beyond 2 weeks post go-live; production support model.
• Infrastructure, Basis, transport landscape provisioning; SSO/IdP integration for external Awardee access (flag: if external identity federation is new, it is a separate workstream with material effort).
• Batch re-validation job (SO-010-010-140) — assumed E006-owned; if assigned to E008, add 5–8 PD.
Top Risk Drivers on the Estimate
• OI-2 Un-Cancel scope (toggle provided): cross-object with E006/EDI; late confirmation converts to change order.
• Unmanaged buffer over the standard SD API (1.2): widest single range; detailed spec will narrow it after API pattern spike — recommend a 3–5 PD technical spike early.
• Cascading value helps (2.6): FSD specifies 5-level Contact help; scope-manage sub-dialogs if timeline pressure emerges.
• External identity/SSO for Awardees: excluded here but on the critical path for any external-facing go-live.
• Team RAP/V4 maturity: the ramp lever is real money — staff at least one RAP-experienced lead to compress it.