CDC VTrckS Migration to S/4HANA — Enhancement E008

Mobilization Plan: Immediate Next Actions on Approach Acceptance

Status: DRAFT  ·  Prepared 07/24/2026  ·  Assumes formal acceptance by 07/31/2026; Week 1 (W1) begins 08/03/2026. Phase objective: close all design-blocking decisions, de-risk the highest-uncertainty technical pattern, validate the cockpit UX with real users, complete detailed technical specifications, and re-baseline the estimate — reaching a Build-Start gate in 6 weeks.

# 1. Decision Gates

| Gate | Name | Exit Criteria | Target | Decision Body |
| --- | --- | --- | --- | --- |
| G1 | Approach Acceptance | Solution spec direction endorsed; consistency-log dispositions accepted; mobilization resources committed; owners named for OI-1/2/3 | by 07/31/2026 | Project leadership + CDC business owner |
| G2 | Design Closure | Status dictionary and authorization concept signed; un-cancel and API-channel scope decided; technical specs approved; UX prototype validated (click-parity metric agreed); estimate re-baselined | end W6 (09/11/2026) | Design authority + CDC business owner |
| G3 | Build Start | Detailed development plan approved; team fully staffed; environments/CI ready; funding confirmed against revised estimate | W7 (09/14/2026) | Project leadership |

# 2. Immediate Action Items (W1–W6)

Effort in person-days (PD). Items marked BLOCKER gate the start of build (G3); they are sequenced first deliberately — in this phase, decisions are the critical path, not development.

| ID | Action | Output | Owner / Resources | Effort | Timeline | Depends |
| --- | --- | --- | --- | --- | --- | --- |
| A. Governance & Blocking Decisions |  |  |  |  |  |  |
| A1 | Formal acceptance package: circulate Solution Spec + Consistency Log; close FSD open item (04/21); register CL-01…CL-14 in project RAID log | Signed G1 decision; RAID entries with owners/dates | Solution Architect (SA) + PMO | 1 | W1 |  |
| A2 | Status dictionary workshop and ratification (OI-1, CL-03): codes 1A–1G, names, meanings, transitions, set-by roles, user-selectable subset BLOCKER | Ratified status dictionary v1.0, referenced by E006/E008/BPD | SA (lead), E006 functional lead, CDC business owner, process team | 3 (across parties) | W1–W2 |  |
| A3 | Authorization concept: draft 3-tier model, jurisdiction mapping (Grantee↔Sales Office), action-level restrictions; security review; sign-off (OI-3, CL-02) BLOCKER | Approved authorization concept + PFCG role design | SA (draft), Security lead (review), CDC ISSO as needed | 4 | W1–W3 |  |
| A4 | Un-cancel scope decision (OI-2, CL-01): joint session E006 + integration/EDI + CDC business; decide in/out; if in — confirm budget/SPC re-commitment rules, notification mechanism, audit-trail need BLOCKER | Signed scope decision; CR if in-scope; estimate toggle set accordingly | SA, E006 lead, Integration lead, CDC business owner | 2 | W2–W3 | A1 |
| A5 | API channel ownership (OI-4, CL-04): confirm RICE line, Status Service API ownership, comm-scenario approach; submit BPD correction for tasks -030/-050 | Documented channel scope; corrected BPD taxonomy | Integration lead + SA + process team | 2 | W2–W3 | A1 |
| A6 | Load & performance figures (OI-5, CL-11): peak concurrency, seasonal order volumes, line-item stats, search volumes from CDC ops | Signed NFR inputs; search-projection strategy decision | PMO (collect), CDC ops, SA (derive strategy) | 2 | W2–W4 |  |
| A7 | Print/forms ownership (OI-6) and naming/launchpad model (OI-7): app IDs, service/BO names per RICE conventions, catalogs/tiles; schedule BPD training-reference revision | Naming register; launchpad content model; forms RACI | SA + forms workstream + process team | 2 | W3–W4 | A5 |
| B. Technical De-Risking |  |  |  |  |  |  |
| B1 | Technical spike: unmanaged RAP buffer over standard SD sales order API — create/update/read round-trip incl. partners, user status, one bound action; document the pattern [strongly recommended before spec commit] | Working pattern PoC; estimate line 1.2 range narrowed; go/no-go on pattern variants | Senior RAP developer + SA (review) | 4 | W1–W2 | env access |
| B2 | Environment readiness: dev system access for team, ADT/BAS tooling, transport routes, ATC/CI with S/4-readiness variants, comm-arrangement sandbox for API | Ready dev landscape; CI green on skeleton objects | Basis + Dev leads + PMO | 4 | W1–W3 |  |
| B3 | Verify corrected data-model mappings on target release/FPS (OI-8, CL-06); confirm status-framework surfacing approach for field control | Confirmed mapping annex to tech spec | Senior RAP developer | 1 | W2 | B2 |
| C. UX Validation |  |  |  |  |  |  |
| C1 | Baseline measurement: record CRM_UI task flows with 2–3 power users; count interactions for standard order (header + line + IoH) — this number becomes the acceptance criterion | Documented click-parity baseline | UX designer + SA + CDC/Awardee pilot users | 2 | W1–W2 |  |
| C2 | Cockpit wireframes → interactive prototype (single working surface, status-driven states, contact popup, IoH block) | Clickable prototype v1 | UX designer (lead) + UI5 lead | 8 | W1–W4 | C1 |
| C3 | Customer validation cycle 1 (walkthrough with pilot Awardee/CDC users); incorporate feedback; validation cycle 2; agree click-parity metric formally | Validated design; signed UX acceptance criterion | UX designer + SA + pilot users | 4 | W4–W6 | C2 |
| D. Detailed Technical Specifications & Re-Baseline |  |  |  |  |  |  |
| D1 | Backend technical spec: BO model, CDS views, behavior (validations/determinations/feature control/auth), all actions incl. matrix and E006 interfaces | Approved backend tech spec | Senior RAP dev + SA | 5 | W3–W6 | A2, A3, B1 |
| D2 | Frontend technical spec: cockpit architecture, section components, value-help fragments, message/side-effect handling, 508 approach; List Report spec | Approved frontend tech spec | UI5 lead + UX designer + SA | 4 | W4–W6 | C2 |
| D3 | API technical spec: Web API binding, async contract (acceptance/correlation/status), auth mapping, consumer onboarding | Approved API tech spec | Integration lead + Senior RAP dev | 3 | W4–W6 | A5 |
| D4 | Estimate re-baseline: replace ROM with budgetary estimate from tech specs; retire 15% ROM contingency; set toggles per A4/A5 outcomes; update resource plan | Revised estimate + funding request for G3 | SA + PMO | 2 | W6 | D1–D3 |
| D5 | Detailed development plan (see §4) for G3 approval | Approved development plan | SA + PMO + dev leads | 3 | W5–W6 | D1–D3 |

# 3. Resource Loading (W1–W6)

| Role | Allocation | Focus |
| --- | --- | --- |
| Solution Architect | 60–70% | Decision workshops (A2–A5), spec ownership and reviews, spike review, prototype validation, estimate re-baseline, development plan |
| Senior RAP Developer | 60% | Spike B1, data-model verification, backend tech spec, API spec support — staffing an experienced RAP lead here is what retires the 10% ramp-up lever |
| SAPUI5 Lead | 40% | Prototype build with UX, frontend tech spec, environment/tooling for UI stack |
| UX Designer | 50% | Baseline measurement, wireframes/prototype, validation cycles |
| E006 Functional Lead | ~15% | Status dictionary, un-cancel rules, validation interface contract |
| Integration Lead | ~15% | API/Status-Service ownership, EDI touchpoints for un-cancel, comm scenarios |
| Security Lead | ~10% | Authorization concept review and sign-off |
| Basis | ~10% | Environments, transports, CI |
| PMO | ~20% | RAID, gate logistics, load-figure collection, funding package |
| CDC business owner / pilot users | workshops + 2 validation sessions | Decisions A2/A4; prototype validation C3 — their calendar availability is a genuine schedule risk; book sessions in W1 |

Full build team (2 RAP + 2 UI5 + shared QA) onboards at G3 / W7. Note the phase is decision-heavy: total consultant effort ≈ 45–55 PD across six weeks — small spend, large de-risking.

# 4. Detailed Development Plan — Required Content (produced in D5, approved at G3)

On formal acceptance, the development plan is built from the technical specs and must contain, at minimum:

- Scope refinement & finalization: per-FR scope confirmation against the ratified status dictionary and signed authorization concept; disposition of every estimate toggle (un-cancel, API channel); formal change-control baseline of FR-01…FR-12 so post-G3 additions are CRs, not drift.

- Estimate refinement: re-baseline from ROM (−25/+75%) to budgetary class using tech-spec detail and B1 spike results; retire the 15% ROM contingency; publish per-sprint burn expectations; define the re-estimation trigger (any CR > 5 PD or any gate slip > 2 weeks).

- Build sequencing: backend-first with early service stubs so the cockpit consumes real metadata from sprint 2; indicative 2-week sprints — S1–S2 BO core + CRUD, S3–S4 feature control/auth + first actions, S3–S6 cockpit sections, S4 List Report, S5–S6 remaining actions + value helps, S6–S7 API binding, S7–S8 hardening. Early-ship option: search/display can UAT ahead of the full cockpit.

- Test strategy & calendar: EML unit gates per backend sprint; OPA5/QUnit per UI sprint; FUT scenarios 1–25 mapped to sprints; SIT window with E006/E007/EDI (un-cancel/ASN is cross-object — reserve SIT capacity); UAT with pilot users incl. 508 verification and the click-parity measurement (Test 25).

- Governance: entry/exit criteria per sprint and gate; RAID carry-over from the consistency log; escalation path for E006 interface slippage (the top external dependency).